## Summary
Part I: 5-Year Integrated Vegetation Management Plan Spreadsheet ----------------------- NATIONAL FOREST
FY | Forest | PROJECT NAME | Location in Lat/Long | Project Phase | Implementation BLI | CWPP Implemented | Planned NEPA Completion Date | Participation by Partners | Watershed Analysis? | Total Acres to be Treated | Sale Volume, CCF | Biomass in Green Tons * | WUI Acres | NON-WUI Acres | WTRSHD-RESTR-ANN Acres | Implementation Tool(s)
12 |  | Summary (formula - don't enter data in this row) | [7 empty] | 10164 | 23800 | 71400 | 2268 | 7896 | 8062
13 |  | Summary (formula - don't enter data in this row) | [7 empty] | 10823 | 12000 | 36000 | 3588 | 7235 | 6689
14 |  | Summary (formula - don't enter data in this row) | [7 empty] | 21131 | 30000 | 90000 | 6375 | 14476 | 17630
15 |  | Summary (formula - don't enter data in this row) | [7 empty] | 23351 | 24120 | 72360 | 6727 | 16624 | 17024
16 |  | Summary (formula - don't enter data in this row) | [7 empty] | 24403 | 22960 | 68880 | 10660 | 13743 | 14893

## FY12
Part I: 5-Year Integrated Vegetation Management Plan Spreadsheet CARIBOU-TARGHEE NATIONAL FOREST
FY | Forest | DISTRICT | PROJECT NAME | Location in Lat/Long | Project Phase | Implementation BLI | CWPP Implemented | Planned NEPA Completion Date | Participation by Partners | Watershed Analysis? | Total Acres to be Treated | Sale Volume, CCF | Biomass in Green Tons * | WUI Acres | NON-WUI Acres | WTRSHD-RSTR-ANN Acres | Implementation Tool(s)
12 | Total |  | Summary (formula - don't enter data in this row) | [7 empty] | 10164 | 23800 | 71400 | 2268 | 7896 | 8062
12 | 15 | 53 | Three Basin |  | Implementation | NFRR |  |  |  |  | 523 | 8300 | 24900 |  | 523 | 523 | TSC
12 | 15 | 53 | Honok |  | Implementation | WFHF |  |  |  |  | 26 |  | 0 | 26 |  |  | FA
12 | 15 | 55 | Slug Creek |  | Implementation | NFRR |  |  |  |  | 559 |  | 0 |  | 559 | 559 | FA
12 | 15 | 53/55/57 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
12 | 15 | 53 | Soda Peak |  | Implementation | NFRR |  |  |  |  | 283 |  | 0 |  | 283 | 283 | FA
12 | 15 | 53 | Maple Burn |  | Implementation | WFHF |  |  |  |  | 150 |  | 0 | 150 |  |  | FA
12 | 15 | 53 | Clear Creek |  | Implementation | WFHF |  |  |  |  | 90 |  | 0 | 90 |  |  | FA
12 | 15 | 57 | Pebble Creek Mowing |  | Implementation | WFHF |  |  |  |  | 95 |  | 0 | 95 |  |  | FA
12 | 15 | 57 | Nordic Center Mowing |  | Implementation | WFHF |  |  |  |  | 65 |  | 0 | 65 |  |  | FA
12 | 15 | 57 | Bannock Creek GS |  | Implementation | WFHF |  |  |  |  | 54 |  | 0 | 54 |  |  | FA
12 | 15 | 57 | Rowley Canyon Rx |  | Implementation | NFRR |  |  |  |  | 3 |  | 0 |  | 3 | 3 | FA
12 | 15 | 53 | Franklin Basin 2/3 |  | Implementation | NFRR |  |  |  |  | 300 |  | 0 |  | 300 | 300 | FA
12 | 15 | 53 | Hollows |  | Implementation | WFHF |  |  |  |  | 40 |  | 0 | 40 |  |  | FA
12 | 15 | 53 | Paris Springs |  | Implementation | WFHF |  |  |  |  | 30 |  | 0 | 30 |  |  | FA
12 | 15 | 53 | Williams Bear |  | Implementation | NFRR |  |  |  |  | 274 |  | 0 |  | 274 | 274 | FA
12 | 15 | 53 | Willow Flat |  | Implementation | NFRR |  |  |  |  | 438 |  | 0 | 438 |  |  | FA
12 | 15 | 53 | Twin Creek Piles |  | Implementation | NFRR |  |  |  |  | 16 |  | 0 | 16 |  | 16 | FA
12 | 15 | 57 | Pebble Creek Piles |  | Implementation | WFHF |  |  |  |  | 69 |  | 0 | 69 |  |  | FA
12 | 15 | 57 | South Mink |  | Implementation | WFHF |  |  |  |  | 24 |  | 0 | 24 |  |  | FA
12 | 15 | 51/52/54/56 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | FA
12 | 15 | 51 | WBP Fuel Reduction |  | Implementation | NFRR |  |  |  |  | 176 |  | 0 |  | 176 | 176 | FA
12 | 15 | 52 | Green Canyon Fuel Break |  | Implementation | Multi + WFHF |  |  |  |  | 73 |  | 0 | 36 | 37 | 37 | FA
12 | 15 | 52 | Raynolds Pass Burn |  | Implementation | Multi + WFHF |  |  |  |  | 400 |  | 0 | 400 |  |  | FA
12 | 15 | 52 | Split Creek Thinning |  | Implementation | NFRR |  |  |  |  | 2891 |  | 0 |  | 2891 | 2891 | FA
12 | 15 | 52 | Communication Site |  | Implementation | WFHF |  |  |  |  | 15 |  | 0 | 15 |  |  | FA
12 | 15 | 54 | Sheep Creek Rx |  | Implementation | WFHF |  |  |  |  | 370 |  | 0 | 370 |  |  | FA
12 | 15 | 54 | Fall Creek Aspen |  | Implementation | NFRR |  |  |  |  | 1200 |  | 0 |  | 1200 | 1200 | FA
12 | 15 | 54 | Flat Iron Aspen |  | Implementation | NFRR |  |  |  |  | 130 |  | 0 | 130 |  | 130 | FA
12 | 15 | 56 | Hill Creek Aspen |  | Implementation | Multi + WFHF |  |  |  |  | 800 |  | 0 | 200 | 600 | 600 | FA
12 | 15 | 56 | Red Creek |  | Implementation | NFRR |  |  |  |  | 250 |  | 0 |  | 250 | 250 | FA
12 | 15 | 56 | Horsecreek Aspen |  | Implementation | WFHF |  |  |  |  | 20 |  | 0 | 20 |  | 20 | FA
12 |  | 53 | Mine Road |  | Implementation | NFRR | [5 empty] | 3500 | 10500
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
12
5-YEAR INTEGRATED VEGETATION MANAGEMENT PLAN SPREADSHEET INSTRUCTIONS
GENERAL INSTRUCTIONS
The spreadsheet is designed so that all the Forest’s reports can be easily combined into one report. Please use the format provided. Do not add extra columns or spaces.
It is understood that this spreadsheet represents a strategic plan that is dynamic, and may necessitate changes as opportunities or barriers arise.
Submit only one copy of the report for each Forest, rather than having individual districts submit reports separately.
Each project should at least have "planning" or "implementation" displayed in column F.
Provide acreage numbers in columns O, P and Q only when the project phase in column F is "implementation".
Populate column I only when the project phase in column F is "planning".
COLUMN
| A) | FY: enter projects by Fiscal Year. Each spreadsheet tab represents a FY.
| B) | Forest: enter the two digit Forest number:
01 - Ashley; 02 - Boise; 03 - Bridger-Teton; 07 - Dixie; 08 - Fishlake; 10 - Manti-LaSal; 12 - Payette; 13 - Salmon-Challis; 14 - Sawtooth;
15 - Caribou-Targhee; 17 - Humboldt-Toiyabe; 19 - Uinta-Wasatch-Cache.
| C) | District: enter the name of the Ranger District, e.g. Emmett.
| D) | Project Name: enter the project name(project name should match project name in the E-SOPA database. Salvage sales will include "Salvage" in the project name).
| E) | Lat/Long: enter location in lat/long coordinates.
| F) | Project Phase: enter the phase (planning, implementation, monitoring) from the pull down list (NEPA is considered planning).
| G) | Implementation BLI: enter the implementation BLI from the pull down list. NEPA is the only project that may be multi-financed.
For NEPA with more than one BLI, select Multi+WFHF or Multi-no WFHF as applicable.
| H) | CWPP Implemented: Community Wildfire Protection Plan has been implemented, Y or N or NA .
| I) | Planned NEPA Completion Date: enter date decision document is to be signed(if decision is already signed put "Done").
| J) | Participation by Partners: Indicate if there is any funding for the project coming from Forest Service Partners, Y or N.
| K) | Watershed Analysis?: Is this project part of a formal landscape plan or watershed analysis? Y or N
| L) | Total Acres to beTreated: enter the total acres treated for project in the fiscal year. Enter only acres receiving treatment (as opposed to the total project area).
If project NEPA has not been completed, enter anticipated acres of treatment per the proposed action.
| M) | Sale Volume, CCF: enter the sale volume, if any, in hundreds of cubic feet (CCF). NOTE: about 200 cubic feet, or two CCF's equal
1,000 board feet, and one CCF approximates a cord of wood).
| N) | Biomass in Green Tons: Include an estimate of green tons of biomass produced from this project (1 CCF = 3 Green Tons).
| O) | WUI Acres: enter the acres of fuels treatment within the Wildland Urban Interface (WUI).
| P) | NON-WUI Acres: enter the acres of fuels treatment outside the Wildland Urban Interface (NON-WUI).
| Q) | WTRSHD-RSTR-ANN Acres: enter the number of acres of Watershed Restored Annually.
| R) | Implementation Tool(s): enter implementation tool code(s): A = Agreement; CS = Service Contract; CSW = Stewardship Contract.
TSC = Timber Sale Contract; FA = Force Account

## FY13
Part I: 5-Year Integrated Vegetation Management Plan Spreadsheet CARIBOU-TARGHEE NATIONAL FOREST
FY | Forest | DISTRICT | PROJECT NAME | Location in Lat/Long | Project Phase | Implementation BLI | CWPP Implemented | Planned NEPA Completion Date | Participation by Partners | Watershed Analysis? | Total Acres to be Treated | Sale Volume, CCF | Biomass in Green Tons * | WUI Acres | NON-WUI Acres | WTRSHD-RSTR-ANN Acres | Implementation Tool(s)
13 | Total |  | Summary (formula - don't enter data in this row) | [7 empty] | 10823 | 12000 | 36000 | 3588 | 7235 | 6689
13 | 15 | 53 | Honok |  | Implementation | WFHF |  |  |  |  | 75 |  | 0 | 75 |  |  | FA
13 | 15 | 53 | St. Charles N Fork |  | Implementation | NFRR |  |  |  |  | 425 |  | 0 |  | 425 | 425 | FA
13 | 15 | 53 | RCD |  | Implementation | WFHF |  |  |  |  | 120 |  | 0 | 120 |  |  | FA
13 | 15 | 57 | Pebble Creek Mowing |  | Implementation | WFHF |  |  |  |  | 95 |  | 0 | 95 |  |  | FA
13 | 15 | 57 | Nordic Center Mowing |  | Implementation | WFHF |  |  |  |  | 65 |  | 0 | 65 |  |  | FA
13 | 15 | 57 | Pebble Creek piles |  | Implementation | WFHF |  |  |  |  | 23 |  | 0 | 23 |  |  | FA
13 | 15 | 57 | Bird Canyon Fuel Break |  | Implementation | WFHF |  |  |  |  | 100 |  | 0 | 100 |  |  | FA
13 | 15 | 53/55/57 | Firewood |  | Implementation | NFRR |  |  |  |  | 400 | 6000 | 18000 |  | 400 |  | TSC
13 | 15 | 53 | Indian Flat |  | Implementation | WFHF |  |  |  |  | 505 |  | 0 | 505 |  |  | FA
13 | 15 | 53 | 8 mile |  | Implementation | NFRR |  |  |  |  | 81 |  | 0 |  | 81 | 81 | FA
13 | 15 | 57 | Curlew Sagebrush |  | Implementation | NFRR |  |  |  |  | 314 |  | 0 | 314 |  |  | FA
13 | 15 | 57 | Topance Wildlife |  | Implementation | Multi + WFHF |  |  |  |  | 1200 |  | 0 | 600 | 600 | 600 | FA
13 | 15 | 53 | Home Canyon |  | Implementation | NFRR |  |  |  |  | 146 |  | 0 |  | 146 |  | FA
13 | 15 | 53 | Bullavard |  | Implementation | NFRR |  |  |  |  | 543 |  | 0 |  | 543 | 543 | FA
13 | 15 | 53 | Soda Point |  | Implementation | WFHF |  |  |  |  | 90 |  | 0 | 90 |  |  | FA
13 | 15 | 53 | Mill Canyon |  | Implementation | NFRR |  |  |  |  | 50 |  | 0 |  | 50 | 50 | FA
13 | 15 | 53 | Bartlett |  | Implementation | NFRR |  |  |  |  | 40 |  | 0 |  | 40 | 40 | FA
13 | 15 | 53 | Emmigration CG |  | Implementation | NFRR |  |  |  |  | 300 |  | 0 |  | 300 | 300 | FA
13 | 15 | 51/52/54/56 | Firewood |  | Implementation | NFRR |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
13 | 15 | 51 | Dubois PCT |  | Implementation | NFRR |  |  |  |  | 300 |  | 0 |  | 300 | 300 | SC
13 | 15 | 51 | Spring Creek |  | Implementation | WFHF |  |  |  |  | 500 |  | 0 | 500 |  |  | FA
13 | 15 | 52 | Black Canyon TSI |  | Implementation | NFRR |  |  |  |  | 2000 |  | 0 |  | 2000 | 2000 | SC
13 | 15 | 52 | Eccles Fuels Project |  | Implementation | WFHF |  |  |  |  | 154 |  | 0 | 154 |  |  | FA
13 | 15 | 54 | Fall Creek Aspen |  | Implementation | NFRR |  |  |  |  | 750 |  | 0 |  | 750 | 750 | FA
13 | 15 | 54 | Flat Iron Aspen |  | Implementation | WFHF |  |  |  |  | 542 |  | 0 | 542 |  |  | FA
13 | 15 | 54 | Conant Valley Aspen |  | Implementation | WFHF |  |  |  |  | 300 |  | 0 | 300 |  |  | FA
13 | 15 | 56 | Red Creek |  | Implementation | NFRR |  |  |  |  | 850 |  | 0 |  | 850 | 850 | FA
13 | 15 | 56 | Badger Creek |  | Implementation | Multi + WFHF |  |  |  |  | 330 |  | 0 | 105 | 225 | 225 | FA
13 | 15 | 56 | Kirkim Hollow |  | Implementation | NFRR |  |  |  |  | 125 |  | 0 |  | 125 | 125 | FA
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
13
5-YEAR INTEGRATED VEGETATION MANAGEMENT PLAN SPREADSHEET INSTRUCTIONS
GENERAL INSTRUCTIONS
The spreadsheet is designed so that all the Forest’s reports can be easily combined into one report. Please use the format provided. Do not add extra columns or spaces.
It is understood that this spreadsheet represents a strategic plan that is dynamic, and may necessitate changes as opportunities or barriers arise.
Submit only one copy of the report for each Forest, rather than having individual districts submit reports separately.
Each project should at least have "planning" or "implementation" displayed in column F.
Provide acreage numbers in columns O, P and Q only when the project phase in column F is "implementation".
Populate column I only when the project phase in column F is "planning".
COLUMN
| A) | FY: enter projects by Fiscal Year. Each spreadsheet tab represents a FY.
| B) | Forest: enter the two digit Forest number:
01 - Ashley; 02 - Boise; 03 - Bridger-Teton; 07 - Dixie; 08 - Fishlake; 10 - Manti-LaSal; 12 - Payette; 13 - Salmon-Challis; 14 - Sawtooth;
15 - Caribou-Targhee; 17 - Humboldt-Toiyabe; 19 - Uinta-Wasatch-Cache.
| C) | District: enter the name of the Ranger District, e.g. Emmett.
| D) | Project Name: enter the project name(project name should match project name in the E-SOPA database. Salvage sales will include "Salvage" in the project name).
| E) | Lat/Long: enter location in lat/long coordinates.
| F) | Project Phase: enter the phase (planning, implementation, monitoring) from the pull down list (NEPA is considered planning).
| G) | Implementation BLI: enter the implementation BLI from the pull down list. NEPA is the only project that may be multi-financed.
For NEPA with more than one BLI, select Multi+WFHF or Multi-no WFHF as applicable.
| H) | CWPP Implemented: Community Wildfire Protection Plan has been implemented, Y or N or NA .
| I) | Planned NEPA Completion Date: enter date decision document is to be signed(if decision is already signed put "Done").
| J) | Participation by Partners: Indicate if there is any funding for the project coming from Forest Service Partners, Y or N.
| K) | Watershed Analysis?: Is this project part of a formal landscape plan or watershed analysis? Y or N
| L) | Total Acres to beTreated: enter the total acres treated for project in the fiscal year. Enter only acres receiving treatment (as opposed to the total project area).
If project NEPA has not been completed, enter anticipated acres of treatment per the proposed action.
| M) | Sale Volume, CCF: enter the sale volume, if any, in hundreds of cubic feet (CCF). NOTE: about 200 cubic feet, or two CCF's equal
1,000 board feet, and one CCF approximates a cord of wood).
| N) | Biomass in Green Tons: Include an estimate of green tons of biomass produced from this project (1 CCF = 3 Green Tons).
| O) | WUI Acres: enter the acres of fuels treatment within the Wildland Urban Interface (WUI).
| P) | NON-WUI Acres: enter the acres of fuels treatment outside the Wildland Urban Interface (NON-WUI).
| Q) | WTRSHD-RSTR-ANN Acres: enter the number of acres of Watershed Restored Annually.
| R) | Implementation Tool(s): enter implementation tool code(s): A = Agreement; CS = Service Contract; CSW = Stewardship Contract.
TSC = Timber Sale Contract; FA = Force Account

## FY14
Part I: 5-Year Integrated Vegetation Management Plan Spreadsheet CARIBOU-TARGHEE NATIONAL FOREST
FY | Forest | DISTRICT | PROJECT NAME | Location in Lat/Long | Project Phase | Implementation BLI | CWPP Implemented | Planned NEPA Completion Date | Participation by Partners | Watershed Analysis? | Total Acres to be Treated | Sale Volume, CCF | Biomass in Green Tons * | WUI Acres | NON-WUI Acres | WTRSHD-RSTR-ANN Acres | Implementation Tool(s)
14 | Total |  | Summary (formula - don't enter data in this row) | [7 empty] | 21131 | 30000 | 90000 | 6375 | 14476 | 17630
14 | 15 | 53 | Minnetonka |  | Implementation | WFHF |  |  |  |  | 300 |  | 0 | 300 |  |  | FA
14 | 15 | 53 | Ephriam |  | Implementation | NFRR |  |  |  |  | 150 |  | 0 |  | 150 | 150 | FA
14 | 15 | 53 | Gateway Powerline |  | Implementation | NFRR |  |  |  |  | 200 | 2000 | 6000 |  | 200 | 200 | TSC
14 | 15 | 57 | South Mink |  | Implementation | NFRR |  |  |  |  | 1000 | 1500 | 4500 |  | 1000 | 1000 | TSC
14 | 15 | 57 | Stone King |  | Implementation | NFRR |  |  |  |  | 600 | 2000 | 6000 | 200 | 400 | 400 | TSC
14 | 15 | 53/55 | TSI |  | Implementation | NFRR |  |  |  |  | 300 |  | 0 |  | 300 | 300 | SC
14 | 15 | 57 | Pebble Creek |  | Implementation | WFHF |  |  |  |  | 95 |  | 0 | 95 |  |  | FA
14 | 15 | 57 | Nordic Center |  | Implementation | WFHF |  |  |  |  | 65 |  | 0 | 65 |  |  | FA
14 | 15 | 57 | Bird Canyon Fuel Break |  | Implementation | WFHF |  |  |  |  | 100 |  | 0 | 100 |  |  | FA
14 | 15 | 57 | Curlew |  | Implementation | WFHF |  |  |  |  | 300 |  | 0 | 300 |  |  | FA
14 | 15 | 53 | St Chuck |  | Implementation | NFRR |  |  |  |  | 1200 |  | 0 |  | 1200 | 1200 | FA
14 | 15 | 53 | Maple |  | Implementation | WFHF |  |  |  |  | 500 |  | 0 | 500 |  |  | FA
14 | 15 | 53/55/57 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
14 | 15 | 51/52/54/56 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
14 | 15 | 51 | Spring Creek |  | Implementation | WFHF |  |  |  |  | 500 |  | 0 | 500 |  |  | FA
14 | 15 | 51 | Fritz Creek |  | Implementation | NFRR |  |  |  |  | 750 |  | 0 |  | 750 | 750 | FA
14 | 15 | 52 | Porcupine Horse Pasture |  | Implementation | NFRR |  |  |  |  | 85 |  | 0 | 85 |  |  | FA
14 | 15 | 52 | Big Horn Estates |  | Implementation | NFRR |  |  |  |  | 203 | 500 | 1500 | 203 |  | 203 | TSC
14 | 15 | 52 | Meadow Creek |  | Implementation | NFRR |  |  |  |  | 260 | 2000 | 6000 | 260 |  | 260 | TSC
14 | 15 | 52 | Bootjack |  | Implementation | NFRR |  |  |  |  | 256 | 2600 | 7800 | 256 |  | 256 | TSC
14 | 15 | 52 | IP Horse pasture |  | Implementation | NFRR |  |  |  |  | 40 |  | 0 | 40 |  |  | FA
14 | 15 | 52 | Watershed 8 |  | Implementation | NFRR |  |  |  |  | 2500 |  | 0 |  | 2500 | 2500 | SC
14 | 15 | 52 | Harriman |  | Implementation | NFRR |  |  |  |  | 2000 |  | 0 |  | 2000 | 2000 | FA
14 | 15 | 52 | West IP WUI |  | Implementation | NFRR |  |  |  |  | 500 | 1000 | 3000 | 500 |  | 500 | TSC
14 | 15 | 54 | Fall Creek Aspen |  | Implementation | NFRR |  |  |  |  | 1500 |  | 0 |  | 1500 | 1500 | FA
14 | 15 | 54 | Flat Iron |  | Implementation | NFRR |  |  |  |  | 1187 |  | 0 |  | 1187 | 1187 | FA
14 | 15 | 54 | Hoffman |  | Implementation | NFRR |  |  |  |  | 500 | 1000 | 3000 | 500 |  | 500 | TSC
14 | 15 | 54 | Conant Valley Aspen |  | Implementation | NFRR |  |  |  |  | 300 |  | 0 | 300 |  |  | FA
14 | 15 | 54 | Kelly Canyon |  | Implementation | NFRR |  |  |  |  | 433 |  | 0 |  | 433 | 433 | FA
14 | 15 | 54 | Alpine West |  | Implementation | Multi + WFHF |  |  |  |  | 400 | 1000 | 3000 | 400 |  | 400 | TSC
14 | 15 | 54 | Eastside Fuel Reduction |  | Implementation | NFRR |  |  |  |  | 785 |  | 0 |  | 785 | 785 | FA
14 | 15 | 54 | Booth Fuel Reduction |  | Implementation | WFHF |  |  |  |  | 500 |  | 0 | 500 |  |  | FA
14 | 15 | 54 | Corral Creek |  | Implementation | Multi + WFHF |  |  |  |  | 752 |  | 0 | 236 | 236 | 236 | FA
14 | 15 | 54 | Blacktail |  | Implementation | NFRR |  |  |  |  | 185 |  | 0 |  | 185 | 185 | FA
14 | 15 | 56 | Red Creek |  | Implementation | NFRR |  |  |  |  | 850 |  | 0 |  | 850 | 850 | FA
14 | 15 | 56 | Teton Canyon |  | Implementation | NFRR |  |  |  |  | 220 | 500 | 1500 | 220 |  | 220 | TSC
14 | 15 | 56 | Packsaddle Fuel Reduction |  | Implementation | NFRR |  |  |  |  | 75 | 300 | 900 | 75 |  | 75 | TSC
14 | 15 | 56 | NE Big Holes |  | Implementation | NFRR |  |  |  |  | 740 | 3600 | 10800 | 740 |  | 740 | TSC
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
14
5-YEAR INTEGRATED VEGETATION MANAGEMENT PLAN SPREADSHEET INSTRUCTIONS
GENERAL INSTRUCTIONS
The spreadsheet is designed so that all the Forest’s reports can be easily combined into one report. Please use the format provided. Do not add extra columns or spaces.
It is understood that this spreadsheet represents a strategic plan that is dynamic, and may necessitate changes as opportunities or barriers arise.
Submit only one copy of the report for each Forest, rather than having individual districts submit reports separately.
Each project should at least have "planning" or "implementation" displayed in column F.
Provide acreage numbers in columns O, P and Q only when the project phase in column F is "implementation".
Populate column I only when the project phase in column F is "planning".
COLUMN
| A) | FY: enter projects by Fiscal Year. Each spreadsheet tab represents a FY.
| B) | Forest: enter the two digit Forest number:
01 - Ashley; 02 - Boise; 03 - Bridger-Teton; 07 - Dixie; 08 - Fishlake; 10 - Manti-LaSal; 12 - Payette; 13 - Salmon-Challis; 14 - Sawtooth;
15 - Caribou-Targhee; 17 - Humboldt-Toiyabe; 19 - Uinta-Wasatch-Cache.
| C) | District: enter the name of the Ranger District, e.g. Emmett.
| D) | Project Name: enter the project name(project name should match project name in the E-SOPA database. Salvage sales will include "Salvage" in the project name).
| E) | Lat/Long: enter location in lat/long coordinates.
| F) | Project Phase: enter the phase (planning, implementation, monitoring) from the pull down list (NEPA is considered planning).
| G) | Implementation BLI: enter the implementation BLI from the pull down list. NEPA is the only project that may be multi-financed.
For NEPA with more than one BLI, select Multi+WFHF or Multi-no WFHF as applicable.
| H) | CWPP Implemented: Community Wildfire Protection Plan has been implemented, Y or N or NA .
| I) | Planned NEPA Completion Date: enter date decision document is to be signed(if decision is already signed put "Done").
| J) | Participation by Partners: Indicate if there is any funding for the project coming from Forest Service Partners, Y or N.
| K) | Watershed Analysis?: Is this project part of a formal landscape plan or watershed analysis? Y or N
| L) | Total Acres to beTreated: enter the total acres treated for project in the fiscal year. Enter only acres receiving treatment (as opposed to the total project area).
If project NEPA has not been completed, enter anticipated acres of treatment per the proposed action.
| M) | Sale Volume, CCF: enter the sale volume, if any, in hundreds of cubic feet (CCF). NOTE: about 200 cubic feet, or two CCF's equal
1,000 board feet, and one CCF approximates a cord of wood).
| N) | Biomass in Green Tons: Include an estimate of green tons of biomass produced from this project (1 CCF = 3 Green Tons).
| O) | WUI Acres: enter the acres of fuels treatment within the Wildland Urban Interface (WUI).
| P) | NON-WUI Acres: enter the acres of fuels treatment outside the Wildland Urban Interface (NON-WUI).
| Q) | WTRSHD-RSTR-ANN Acres: enter the number of acres of Watershed Restored Annually.
| R) | Implementation Tool(s): enter implementation tool code(s): A = Agreement; CS = Service Contract; CSW = Stewardship Contract.
TSC = Timber Sale Contract; FA = Force Account

## FY15
Part I: 5-Year Integrated Vegetation Management Plan Spreadsheet CARIBOU-TARGHEE NATIONAL FOREST
FY | Forest | DISTRICT | PROJECT NAME | Location in Lat/Long | Project Phase | Implementation BLI | CWPP Implemented | Planned NEPA Completion Date | Participation by Partners | Watershed Analysis? | Total Acres to be Treated | Sale Volume, CCF | Biomass in Green Tons * | WUI Acres | NON-WUI Acres | WTRSHD-RSTR-ANN Acres | Implementation Tool(s)
15 | Total |  | Summary (formula - don't enter data in this row) | [7 empty] | 23351 | 24120 | 72360 | 6727 | 16624 | 17024
15 | 15 | 53 | Sugar Creek contract |  | Implementation | WFHF |  |  |  |  | 800 |  | 0 | 800 |  |  | FA
15 | 15 | 53 | Ephriam aspen |  | Implementation | NFRR |  |  |  |  | 400 |  | 0 |  | 400 |  | FA
15 | 15 | 53 | Strawberry Aspen |  | Implementation | NFRR |  |  |  |  | 500 |  | 0 |  | 500 |  | FA
15 | 15 | 53 | Main Canyon |  | Implementation | Multi + WFHF |  |  |  |  | 500 | 1000 | 3000 | 100 | 400 | 500 | TSC
15 | 15 | 53 | Hollows |  | Implementation | Multi + WFHF |  |  |  |  | 208 |  | 0 | 100 | 108 | 108 | FA
15 | 15 | 55 | Henry Aspen |  | Implementation | NFRR |  |  |  |  | 100 |  | 0 |  | 100 | 100 | FA
15 | 15 | 55 | Tin Cup Mountain |  | Implementation | NFRR |  |  |  |  | 1000 |  | 0 |  | 1000 | 1000 | FA
15 | 15 | 55 | Aspen Range TS |  | Implementation | NFRR |  |  |  |  | 473 | 6000 | 18000 |  | 473 | 473 | TSC
15 | 15 | 57 | Dry Gulch |  | Implementation | NFRR |  |  |  |  | 2500 |  | 0 |  | 2500 | 2500 | FA
15 | 15 | 53/55/57 | SZ TSI |  | Implementation | NFRR |  |  |  |  | 200 |  | 0 |  | 200 | 200 | SC
15 | 15 | 55 | Gravel Creek CG |  | Implementation | WFHF |  |  |  |  | 200 |  | 0 | 200 |  |  | FA
15 | 15 | 53 | Cachce Roads |  | Implementation | NFRR |  |  |  |  | 250 |  | 0 |  | 250 | 250 | FA
15 | 15 | 57 | Pebble Creek Mowing |  | Implementation | WFHF |  |  |  |  | 95 |  | 0 | 95 |  |  | FA
15 | 15 | 57 | Nordic Center Mowing |  | Implementation | WFHF |  |  |  |  | 65 |  | 0 | 65 |  |  | FA
15 | 15 | 57 | Scout Mountain maintenance |  | Implementation | WFHF |  |  |  |  | 10 |  | 0 | 10 |  |  | FA
15 | 15 | 57 | Curlew Sagebrush protection |  | Implementation | WFHF |  |  |  |  | 300 |  | 0 | 300 |  |  | FA
15 | 15 | 53/55/57 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
15 | 15 | 51/52/54/56 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
15 | 15 | 51 | Dry Creek |  | Implementation | NFRR |  |  |  |  | 250 | 1860 | 5580 |  | 250 | 250 | TSC
15 | 15 | 51 | Porcupine |  | Implementation | NFRR |  |  |  |  | 200 | 960 | 2880 |  | 200 | 200 | TSC
15 | 15 | 51 | Three Mile |  | Implementation | NFRR |  |  |  |  | 1500 |  | 0 |  | 1500 | 1500 | FA
15 | 15 | 51 | Timber Canyon |  | Implementation | NFRR |  |  |  |  | 1500 |  | 0 |  | 1500 | 1500 | FA
15 | 15 | 52 | Watershed 8 TSI |  | Implementation | NFRR |  |  |  |  | 2500 |  | 0 |  | 2500 | 2500 | SC
15 | 15 | 52 | Aspen Reclamation |  | Implementation | NFRR |  |  |  |  | 100 |  | 0 |  | 100 | 100 | FA
15 | 15 | 52 | Thurmon |  | Implementation | Multi + WFHF |  |  |  |  | 2000 |  | 0 | 1000 | 1000 | 2000 | FA
15 | 15 | 54 | Fall Creek |  | Implementation | NFRR |  |  |  |  | 750 |  | 0 |  | 750 | 750 | FA
15 | 15 | 54 | Alpine West |  | Implementation | Multi + WFHF |  |  |  |  | 700 |  | 0 | 200 | 500 | 500 | FA
15 | 15 | 54 | Blacktail |  | Implementation | Multi + WFHF |  |  |  |  | 185 |  | 0 | 92 | 93 | 93 | FA
15 | 15 | 54 | Calf Hollow |  | Implementation | NFRR |  |  |  |  | 150 |  | 0 |  | 150 | 150 | FA
15 | 15 | 56 | Red Creek |  | Implementation | NFRR |  |  |  |  | 850 |  | 0 |  | 850 | 850 | FA
15 | 15 | 56 | Grand Targhee |  | Implementation | NFRR |  |  |  |  | 550 | 800 | 2400 | 550 |  |  | TSC
15 | 15 | 56 | Teton Pass |  | Implementation | NFRR |  |  |  |  | 200 | 500 | 1500 | 200 |  | 200 | TSC
15 | 15 | 56 | SE Big Holes |  | Implementation | NFRR |  |  |  |  | 3515 | 1000 | 3000 | 3015 | 500 | 500 | TSC
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
15
5-YEAR INTEGRATED VEGETATION MANAGEMENT PLAN SPREADSHEET INSTRUCTIONS
GENERAL INSTRUCTIONS
The spreadsheet is designed so that all the Forest’s reports can be easily combined into one report. Please use the format provided. Do not add extra columns or spaces.
It is understood that this spreadsheet represents a strategic plan that is dynamic, and may necessitate changes as opportunities or barriers arise.
Submit only one copy of the report for each Forest, rather than having individual districts submit reports separately.
Each project should at least have "planning" or "implementation" displayed in column F.
Provide acreage numbers in columns O, P and Q only when the project phase in column F is "implementation".
Populate column I only when the project phase in column F is "planning".
COLUMN
| A) | FY: enter projects by Fiscal Year. Each spreadsheet tab represents a FY.
| B) | Forest: enter the two digit Forest number:
01 - Ashley; 02 - Boise; 03 - Bridger-Teton; 07 - Dixie; 08 - Fishlake; 10 - Manti-LaSal; 12 - Payette; 13 - Salmon-Challis; 14 - Sawtooth;
15 - Caribou-Targhee; 17 - Humboldt-Toiyabe; 19 - Uinta-Wasatch-Cache.
| C) | District: enter the name of the Ranger District, e.g. Emmett.
| D) | Project Name: enter the project name(project name should match project name in the E-SOPA database. Salvage sales will include "Salvage" in the project name).
| E) | Lat/Long: enter location in lat/long coordinates.
| F) | Project Phase: enter the phase (planning, implementation, monitoring) from the pull down list (NEPA is considered planning).
| G) | Implementation BLI: enter the implementation BLI from the pull down list. NEPA is the only project that may be multi-financed.
For NEPA with more than one BLI, select Multi+WFHF or Multi-no WFHF as applicable.
| H) | CWPP Implemented: Community Wildfire Protection Plan has been implemented, Y or N or NA .
| I) | Planned NEPA Completion Date: enter date decision document is to be signed(if decision is already signed put "Done").
| J) | Participation by Partners: Indicate if there is any funding for the project coming from Forest Service Partners, Y or N.
| K) | Watershed Analysis?: Is this project part of a formal landscape plan or watershed analysis? Y or N
| L) | Total Acres to beTreated: enter the total acres treated for project in the fiscal year. Enter only acres receiving treatment (as opposed to the total project area).
If project NEPA has not been completed, enter anticipated acres of treatment per the proposed action.
| M) | Sale Volume, CCF: enter the sale volume, if any, in hundreds of cubic feet (CCF). NOTE: about 200 cubic feet, or two CCF's equal
1,000 board feet, and one CCF approximates a cord of wood).
| N) | Biomass in Green Tons: Include an estimate of green tons of biomass produced from this project (1 CCF = 3 Green Tons).
| O) | WUI Acres: enter the acres of fuels treatment within the Wildland Urban Interface (WUI).
| P) | NON-WUI Acres: enter the acres of fuels treatment outside the Wildland Urban Interface (NON-WUI).
| Q) | WTRSHD-RSTR-ANN Acres: enter the number of acres of Watershed Restored Annually.
| R) | Implementation Tool(s): enter implementation tool code(s): A = Agreement; CS = Service Contract; CSW = Stewardship Contract.
TSC = Timber Sale Contract; FA = Force Account

## FY16
Part I: 5-Year Integrated Vegetation Management Plan Spreadsheet CARIBOU-TARGHEE NATIONAL FOREST
FY | Forest | DISTRICT | PROJECT NAME | Location in Lat/Long | Project Phase | Implementation BLI | CWPP Implemented | Planned NEPA Completion Date | Participation by Partners | Watershed Analysis? | Total Acres to be Treated | Sale Volume, CCF | Biomass in Green Tons * | WUI Acres | NON-WUI Acres | WTRSHD-RSTR-ANN Acres | Implementation Tool(s)
16 | Total |  | Summary (formula - don't enter data in this row) | [7 empty] | 24403 | 22960 | 68880 | 10660 | 13743 | 14893
16 | 15 | 53 | Sugar Creek burn |  | Implementation | WFHF |  |  |  |  | 800 |  | 0 | 800 |  |  | FA
16 | 15 | 53 | Strawberry Aspen |  | Implementation | NFRR |  |  |  |  | 1000 |  | 0 |  | 1000 | 1000 | FA
16 | 15 | 53 | Boulevard |  | Implementation | NFRR |  |  |  |  | 200 | 4000 | 12000 | 200 |  | 200 | TSC
16 | 15 | 53 | Hollows |  | Implementation | NFRR |  |  |  |  | 500 |  | 0 | 300 | 200 | 200 | FA
16 | 15 | 55 | Henry Aspen |  | Implementation | NFRR |  |  |  |  | 543 |  | 0 |  | 543 | 543 | FA
16 | 15 | 55 | Soda Front |  | Implementation | NFRR |  |  |  |  | 1000 |  | 0 |  | 1000 | 1000 | FA
| 15 | 55 | Bridge Creek |  | Implementation | Multi + WFHF |  |  |  |  | 250 | 3000 | 9000 | 250 |  | 250 | TSC
16 | 15 | 55 | Lanes Creek |  | Implementation | NFRR |  |  |  |  | 250 | 2000 | 6000 |  | 250 | 250 | TSC
16 | 15 | 57 | Clifton Basin RX |  | Implementation | NFRR |  |  |  |  | 1000 |  | 0 |  | 1000 | 1000 | FA
16 | 15 | 57 | Potter Creek |  | Implementation | NFRR |  |  |  |  | 1200 |  | 0 |  | 1200 | 1200 | FA
16 | 15 | 57 | Curlew |  | Implementation | WFHF |  |  |  |  | 300 |  | 0 | 300 |  |  | FA
16 | 15 | 53/55/57 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | FA
16 | 15 | 51 | Dry Creek 2 |  | Implementation | NFRR |  |  |  |  | 150 | 960 | 2880 |  | 150 | 150 | TSC
16 | 15 | 51 | Left Fork Calf Crk |  | Implementation | Multi + WFHF |  |  |  |  | 1500 |  | 0 | 750 | 750 | 750 | FA
16 | 15 | 52 | Fall River |  | Implementation | Multi + WFHF |  |  |  |  | 2000 | 500 | 1500 | 1000 | 1000 | 1000 | TSC
16 | 15 | 52 | Bishop Mtn |  | Implementation | NFRR |  |  |  |  | 500 | 250 | 750 |  | 500 | 500 | TSC
16 | 15 | 54 | Rainey Creek/Fuel Break/Trails |  | Implementation | NFRR |  |  |  |  | 2100 |  | 0 |  | 2100 | 2100 | FA
16 | 15 | 54 | Alpine West Hazardous Fuels - RX, Unit 1 |  | Implementation | WFHF |  |  |  |  | 600 |  | 0 | 600 |  | 600 | FA
16 | 15 | 54 | Echo Canyon WUI |  | Implementation | Multi + WFHF |  |  |  |  | 2100 |  | 0 | 1550 | 550 | 550 | FA
16 | 15 | 54 | Jack Branch |  | Implementation | Multi + WFHF |  |  |  |  | 4800 |  | 0 | 2700 | 2100 | 2100 | FA
16 | 15 | 54 | Maple Grove Fuel Break - Thin/Pile |  | Implementation | WFHF |  |  |  |  | 110 |  | 0 | 110 |  |  | FA
16 | 15 | 56 | Red Ck RX Fire Project, Unit 6, RX |  | Implementation | NFRR |  |  |  |  | 600 |  | 0 |  | 600 | 600 | FA
16 | 15 | 56 | Teton Pass Fuels Red/BLM Rx Fire Unit4 |  | Implementation | WFHF |  |  |  |  | 2000 |  | 0 | 2000 |  |  | FA
16 | 15 | 56 | Teton Pass Fuels Red-Trail Ck TS |  | Implementation | NFRR |  |  |  |  | 100 | 250 | 750 | 100 |  | 100 | TSC
16 | 15 | 51/52/54/56 | Firewood |  | Implementation | SSSS |  |  |  |  | 400 | 6000 | 18000 |  | 400 | 400 | TSC
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
5-YEAR INTEGRATED VEGETATION MANAGEMENT PLAN SPREADSHEET INSTRUCTIONS
GENERAL INSTRUCTIONS
The spreadsheet is designed so that all the Forest’s reports can be easily combined into one report. Please use the format provided. Do not add extra columns or spaces.
It is understood that this spreadsheet represents a strategic plan that is dynamic, and may necessitate changes as opportunities or barriers arise.
Submit only one copy of the report for each Forest, rather than having individual districts submit reports separately.
Each project should at least have "planning" or "implementation" displayed in column F.
Provide acreage numbers in columns O, P and Q only when the project phase in column F is "implementation".
Populate column I only when the project phase in column F is "planning".
COLUMN
| A) | FY: enter projects by Fiscal Year. Each spreadsheet tab represents a FY.
| B) | Forest: enter the two digit Forest number:
01 - Ashley; 02 - Boise; 03 - Bridger-Teton; 07 - Dixie; 08 - Fishlake; 10 - Manti-LaSal; 12 - Payette; 13 - Salmon-Challis; 14 - Sawtooth;
15 - Caribou-Targhee; 17 - Humboldt-Toiyabe; 19 - Uinta-Wasatch-Cache.
| C) | District: enter the name of the Ranger District, e.g. Emmett.
| D) | Project Name: enter the project name(project name should match project name in the E-SOPA database. Salvage sales will include "Salvage" in the project name).
| E) | Lat/Long: enter location in lat/long coordinates.
| F) | Project Phase: enter the phase (planning, implementation, monitoring) from the pull down list (NEPA is considered planning).
| G) | Implementation BLI: enter the implementation BLI from the pull down list. NEPA is the only project that may be multi-financed.
For NEPA with more than one BLI, select Multi+WFHF or Multi-no WFHF as applicable.
| H) | CWPP Implemented: Community Wildfire Protection Plan has been implemented, Y or N or NA .
| I) | Planned NEPA Completion Date: enter date decision document is to be signed(if decision is already signed put "Done").
| J) | Participation by Partners: Indicate if there is any funding for the project coming from Forest Service Partners, Y or N.
| K) | Watershed Analysis?: Is this project part of a formal landscape plan or watershed analysis? Y or N
| L) | Total Acres to beTreated: enter the total acres treated for project in the fiscal year. Enter only acres receiving treatment (as opposed to the total project area).
If project NEPA has not been completed, enter anticipated acres of treatment per the proposed action.
| M) | Sale Volume, CCF: enter the sale volume, if any, in hundreds of cubic feet (CCF). NOTE: about 200 cubic feet, or two CCF's equal
1,000 board feet, and one CCF approximates a cord of wood).
| N) | Biomass in Green Tons: Include an estimate of green tons of biomass produced from this project (1 CCF = 3 Green Tons).
| O) | WUI Acres: enter the acres of fuels treatment within the Wildland Urban Interface (WUI).
| P) | NON-WUI Acres: enter the acres of fuels treatment outside the Wildland Urban Interface (NON-WUI).
| Q) | WTRSHD-RSTR-ANN Acres: enter the number of acres of Watershed Restored Annually.
| R) | Implementation Tool(s): enter implementation tool code(s): A = Agreement; CS = Service Contract; CSW = Stewardship Contract.
TSC = Timber Sale Contract; FA = Force Account