## IM&A TG
FY14 | [5 empty] | FY15
April | May | June | July | August | September | October | November | December | January | February | March
1.00 Project Management
| 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update
NFS Director's Briefing | 5/7 PMT Call |  |  | 8/7 PMT Call | NFS Director's Briefing |  | PMT Call |  |  | PMT Call | NFS Director's Briefing
1.64 FY15 IRDB Request
3.00 Draft GW I&M Technical Guide
4.00 Evaluation and Review (See Evaluation and Review Plan v3.1 - 2/29/12)
4.80 Review/Reconciliation Document
|  | 4.90 Final Edits |  |  | IM&A TG v5.0
5.0 Finalize and Publish IM&A Technical Guide
5.10 OC Publication Request
5.20 Organize Pub. Files
5.30 Technical Editoral Review
5.40 Reconcile
5.50 Layout
5.60 Finalize Layout
IM&A TG v6.0
5.80 Revised Tech. Guide Published
IM&A TG v1.0
6.0 Implementation (FS Application Interface/Communication/Training)
6.30 FS/NRM App. Requirements (v1.0) | [5 empty] | 6.30 FS/NRM App. Requirements (v2.0)
6.40 Data Dictionary Edits |  | Revised DD
6.50 NRM/GMO Leadership Engagements
6.60 Comm./Outreach Plan | [6 empty] | 6.50 FS Application Changes
6.70 User Community Briefings
6.90 Training Requirements | [5 empty] | 6.90 Training Program
CT Call 4/10 (2:00) |  |  | CT Call 7/10 (2:00) |  |  | CT Call TBD (2:00) |  |  |  | CT Call TBD (2:00)
ST Call 4/24 (3:00) |  |  | ST Call 7/24 (3:00) |  |  | ST Call TBD (3:00) |  |  |  | ST Call TBD (3:00)
GW IM&A Technical Guide Development |  |  |  | GW Inventory, Monitoring, and Assessment Technical Guide Implementation
Revision of Managing GW Resources Technical Guide (FS-881)

## IM&A TG Task Schedule
1.00 Project Management
Task Description | Start Date | Due Date | Assigned To:
1.4x Quarterly Project Schedule Updates |  | Quarterly | Solem
1.4x Quarterly Project Management Team Call |  | Quarterly | Carlson/Gurrieri/Solem
1.63 - FY15 NRIS POW Request | TBD |  | Chris Carlson
4.00 Evaluation and Review (See Evaluation and Review Plan v3.1 - 2/29/12)
Task Description | Start Date | Due Date | Assigned To:
4.60 - Internal FS Review |  | Done | R/S/A/WO Staffs
4.70 - Partner/Affiliate Review |  | Done | See P&A Review Roster
4.80 - Review Comments/Reconciliation Record | 2014-03-24 | 2014-06-27 | Carlson/Gurrieri/Solem/Giffen
4.90 - Final TG Edits (v5.0) | 2014-06-02 | 2014-09-26 | Carlson/Gurrieri/CT/Solem/Giffen
6.00 Implementation (FS Application Interfaces/Communication/Training)
6.21 Conduct FS Application Dependency Assessment |  | Done | FS Users
6.22 Conduct Geodatabase/Data Dictionary Assessment |  | Done | FS Users
6.221 - TNC Data Dictionary Briefing |  | Done | Kilbourne
6.222 - Utah Geological Survey Briefing |  | Done | Kilbourne
6.30 NRM Requirements Analysis (v1.0) | 2014-03-11 | 2014-07-31 | Spencer/Kilborune/Giffen/Solem
6.40 GIS Data Dictionary Edits | 2014-03-11 | 2014-06-30 | Kilborune/Spencer/Solem
6.50 NRM/GMO Leadership Engagements | 2013-07-01 | Ongoing | Carlson/Solem/Kilborune/Spencer
6.51 - NRM Leadership/Staff Briefings |  | Done | Spencer/Solem/Kilborune/Rorick
6.60 Communication and Outreach Plan | 2013-11-25 | TBD | Carlson/Solem/Giffen
6.70 User Community Briefings | 2013-07-01 | Ongoing | Steering and Core Team Members
6.71 - FS Program Staff Briefings |  | TBD | Steering and Core Team Members
6.90 Training Program Assessment | 2014-04-01 | 2014-09-30 | Gurrieri/Carlson
5.00 Publish Groundwater Inventory and Monitoring Technical Guide
5.10 - Publication Request/Schedule with OC | 2014-08-01 | 2014-08-30 | Carlson/Solem
5.20 - Organize Publication Files (Text/Graphics) | 2014-06-01 | 2014-09-26 | Giffen/Boehnke
5.30 - Technical Editor Review/Document Layout | 2014-10-01 | 2014-12-14 | OC Contractor/Carlson/Giffen
5.40 - Reconcile Editorial Comments | 2014-11-13 | 2014-12-15 | Carlson/Giffen
5.50 - Layout Review | 2014-11-13 | 2014-12-15 | Carlson/Giffen/Boehnke
5.60 - Finalize Content/Layout | 2014-12-16 | 2014-12-15 | OC Contractor/Carlson/Giffen
5.80 - Publish GW I&M TG (Version 1.0) | 2015-12-16 | 2015-03-13 | OC Contractor
5.90 - Distribute TG/Document Repository | 2014-03-16 | 2014-04-30 | Carlson/Gurrieri

## GW Mgmt. TG Revision
FY 14 | [5 empty] | FY15 | [11 empty] | FY16
April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
1.00 Project Management
| 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update |  |  | 1.40 Update
NFS Director's Briefing | PMT Call |  |  | PMT Call | NFS Director's Briefing |  | PMT Call |  |  | PMT Call | NFS Director's Briefing |  | PMT Call |  |  | PMT Call | NFS Director's Briefing |  | PMT Call |  |  | PMT Call | NFS Director's Briefing
[5 empty] | 1.64 FY16 IRDB Request | [11 empty] | 1.64 FY16 IRDB Request
2.00 Requierments Analysis
3.00 Draft GW I&M Technical Guide
4.00 Evaluation and Review
5.0 Finalize and Publish IM&A Technical Guide
6.0 Implementation (FS Application-GIS Requirements/Communication/Training)
CT Call 4/10 (2:00) |  |  | CT Call 7/10 (2:00) |  |  | CT Call TBD (2:00) |  |  |  | CT Call TBD (2:00) |  |  |  | CT Call 6/12 (2:00) |  |  |  | CT Call TBD (2:00) |  |  |  | CT Call TBD (2:00) |  |  |  | CT Call 6/12 (2:00)
ST Call 4/24 (3:00) |  |  | ST Call 7/24 (3:00) |  |  | ST Call TBD (3:00) |  |  |  | ST Call TBD (3:00) |  |  |  | ST Call 6/26 (3:00) |  |  |  | ST Call TBD (3:00) |  |  |  | ST Call TBD (3:00) |  |  |  | ST Call 6/26 (3:00)
Revision Scope
Develop Revised Technical Guide (Draft)
Tech Review
FS & Partner Review
TG Publication
FS Applications/GIS Data Dictionary
Stakeholder Communication and Involvement
Revised Technical Guide (Final)

## CT-ST Meeting Topics
Steering Team/Core Team Call Schedule and Objectives
CT Call Dates | ST Call Dates | CT/ST Meeting Objectives
2014-04-10 | 2014-04-24 | 5.80 - Internal FS and Partner Comment Reconciliation
4.50 - Edits to GW I&M Technical Guide v5.0
6.90 - GW IM&A Technical Guide Implementation
2.20 - Managing GW Resources TG Revision Requirements Analysis (Revision Scope)
2014-07-10 | 2014-07-24 | 6.90 - GW IM&A Technical Guide Implementation
3.10 - Managing GW Resources TG Revision Task Assignment Status Reports
2014-10-16 | 2014-10-30
2015-02-12 | 2015-02-26
Logistics
Calls at: | Calls at: | Conference Call Information
2:00 ET | 3:00 ET | Call In Number: 888-844-9904 Passcode: 8924477
12:00 MT | 1:00 MT | Live Meeting Access Information
2 hrs max | 1 hr. max
Project Management Team Call Schedule
2014-05-07 | 1200 ET/1000 MT
2014-08-07 | 1200 ET/1000 MT
2014-11-05 | 1200 ET/1000 MT
2015-02-04 | 1200 ET/1000 MT