## R6 Powerline Activity Chart
Notification | Class A Activity | Class B Activity | Class C Activity | Class D Activity
Notice, timelines and approval level | Prior Notice. A telephone call or email from the owner or operator to the authorized officer is sufficient prior notice for Class A activities. USFS Response to Prior Notice. Class A activities approved under an operating plan or agreement must be acknowledged (not approved) by the authorized officer by telephone call or email within 24 hours of receipt of prior notice. The owner or operator may proceed with Class A activities upon authorized officer acknowledgment or if the authorized officer does not acknowledge receipt of prior notice within 24 hours. | Prior Notice. The owner or operator may satisfy prior notice for Class B activities conducted under an approved operating plan or agreement by submitting a single project notice or an annual schedule of work that identifies the activities planned for a calendar year. If deemed practical by the authorized officer, the owner or operator may be allowed to submit an annual schedule that covers up to 5 years of Class B activities. An email or letter regarding a single project or an email transmitting an annual schedule of work is sufficient prior notice for Class B activities. USFS Response to Prior Notice. Generally, prior notice for Class B activities will require prior written acknowledgment, rather than approval, by email or letter from the authorized officer. Prior written approval by email or letter from the authorized officer is required for routine maintenance of NFS roads that requires a road use permit. Prior written approval by email or letter from the authorized officer is also required for routine vegetation management unless: a. The owner or operator has submitted an email or letter requesting approval of a single routine vegetation management project or an annual schedule of work for routine vegetation management in accordance with the specified timeframe in the approved operating plan or agreement; b. The proposed routine vegetation management is covered by approval of a proposed operating plan or agreement or by subsequent case-by-case environmental analysis and consultation; and c. The authorized officer has not responded to the request in accordance with the specified timeframe** in the approved operating plan or agreement. (In Oregon and Washington - that timeframe is recommended to be 30 days) Before acknowledging or approving an annual schedule of work for routine vegetation management, the authorized officer should ensure that it complies with the approved operating plan or agreement; determine whether additional authorization may be required for any activities in the annual schedule of work; and determine whether any changes in laws, regulations, or directives have occurred that may expedite or delay the activities in the annual schedule of work. The authorized officer may adjust an annual schedule of work for routine vegetation management to address changed conditions in accordance with section 86, paragraph 3. | Prior Notice. Submission of an application (form FS-299) is required for prior notice of Class C activities. USFS Response to Prior Notice. Per 36 CFR 251.61, Class C activities require prior written approval in a signed letter from the authorized officer. The timeframe for approval will vary based on the complexity of the additional environmental analysis and consultation for listed endangered or threatened species and cultural and historic resources required for Class C activities. A separate special use authorization is not required. However, if Class C activities are approved, the existing powerline facility authorization must be amended to reflect the approved activities. | Prior Notice. Prior notice is not required for Class D activities but is suggested to the extent practicable to allow for any necessary Forest Service actions, such as notification of the State Historic Preservation Office. USFS Response: Prior acknowledgment or approval from the authorized officer is not required for Class D activities. Appropriate prior notice and response are required before conducting other classes of activities in the vicinity of the owner’s or operator’s emergency response. Subsequent Notice. The owner or operator must notify the authorized officer by email of the location and type of Class D activities as soon as practicable, but no later than 24 hours after completion of the activities. Within 30 days of completing Class D activities, the owner or operator must submit to the authorized officer a written report detailing at a minimum the location, type, and scope of the activities conducted, the reason they were conducted, the methods used to conduct them, and the resulting benefits. The owner or operator may be required to conduct consultation under the ESA and NHPA following Class D activities to determine impacts on listed threatened or endangered species or their habitat and cultural and historic resources (FSM 2670). The Forest Service may charge cost recovery fees for any costs incurred by the Agency in connection with consultation required after Class D activities. | **Regarding specified time for Class B activities in the operating plan, this should be negotiated. R6 is recommending the following: Powerline operators should submit their annual plan of work 30 days prior to the scheduled annual meeting. The Authorized Officer should respond within 15 days after the annual meeting. If no annual meeting is planned, then the Authorized Officer should respond within 45 days. If additional review, such as a cultural resource survey, is needed, the response should outline the addition time needed for that review. If additional activities are added after the annual plan of work is approved, the 45 day timeline does not apply.
Activities | Class A Activity | Class B Activity | Class C Activity | Class D Activity | Comments
Description | Class A includes routine activities that are deemed by qualified Forest Service specialists to involve minimal or no ground disturbance or impacts on vegetation inside and outside the linear right-of-way for the powerline facilities and that do not require additional environmental analysis or consultation for listed endangered or threatened species and cultural and historic resources. Examples include but are not limited to mapping and inspections of poles, conductors, and other structures where large equipment, helicopters, or drones would be involved. Class A activities may be restricted during certain times or under certain conditions to prevent adverse environmental, cultural, or species or habitat impacts. | Class B includes routine activities that are deemed by qualified Forest Service specialists to involve minimal ground disturbance and impacts on NFS lands inside and outside the linear right-of-way for the powerline facilities and that do not require additional environmental analysis or consultation for listed endangered or threatened species and cultural and historic resources. Examples include but are not limited to routine vegetation management, routine powerline facility maintenance, routine maintenance of access roads and trails and NFS roads and NFS trails, and routine repair or replacement of fiber optic cable. | Class C activities involve new, changed, or additional uses or areas under 36 CFR 251.61. Due to their complexity, impacts, and scope, Class C activities will typically require additional environmental analysis and consultation for listed endangered or threatened species and cultural and historic resources. Examples include but are not limited to new construction, rerouting of powerline facilities, and refurbishment or replacement of powerline facility components such as conductors, ground wires, and fiber optic cable; non-routine powerline facility maintenance; hazard tree felling or pruning that extends beyond the linear right-of-way for a powerline facility; road and trail construction and reconstruction; non-routine road and trail use and maintenance, such as installation of drainage features, fences, gates, or signs; and installation of fiber optic cable on powerline facilities. | Class D activities include emergency vegetation management and emergency powerline facility maintenance. Class D activities do not require additional environmental analysis and consultation for listed endangered or threatened species and cultural and historic resources. Examples include but are not limited to unplanned felling or pruning of hazard trees to prevent imminent contact with a powerline facility and immediate repair or replacement of powerline facility components that is necessary to restore electrical service. Ensure approved operating plans and agreements require that owners and operators take measures necessary to protect natural resources during emergency operations. Routine vegetation management and powerline facility maintenance should be planned and approved to mitigate Class D activities.
INSPECTIONS
Facility inspection | X
Vegetation inspection | X
Cultural surveys |  |  | X |  | ARPA permit needed
Other resource surveys | X
UAS use in inspections (drones) |  | X |  |  | If using drones, no requirements if not launching or landing on NFS lands. Each company's operating plan should address this process.
Manned aircraft inspections with no related ground operations (landings, sling loads, helisaw) on NFS lands |  |  |  |  | No authorization or notification required.
Manned aircraft inspections with related land operatins (sling loads, landings, helisaw) on NFS lands |  | X | X |  | Level of approval dependent on scope of project. Landing zones will required additional authorization.
ABOVE GROUND LINE POWERLINES
Maintenance and replacement of equipment on poles or towers with no ground disturbance | X
Repair of downed powerline or fiberline |  |  |  | X
Single pole replacement | X | X |  |  | Amount of ground disturbance and location of pole are factors determining the amount of review
Replacement of several poles in one area |  | X
Tower replacement |  | X | X |  | Depending on scope of project.
Emergency repairs within ROW |  |  |  | X | Typically storm response
Construction of new overhead powerline |  |  | X
Relocation of overhead powerline |  |  | X
UNDERGROUND POWERLINES
Maintenance of line through vault boxes | X
Replacement of aged buried line |  | X | X |  | Depends on if the line will simply be pulled through existing conduit or replacment line will be buried along side new line
Construction of new buried powerline |  |  | X
Relocation of buried powerline |  |  | X
Overhead line converted to buried powerline |  |  | X
VEGETATION MANAGEMENT
Planned vegetation clearing cycle |  | X
"touch up" vegetation clearing between cycles |  | X
Hazard trees within the ROW prunned, topped or felled |  | X
Hazard trees outside of the ROW prunned, topped or felled. |  | x | X |  | This is dependent on the scope of work such a location and number of hazard trees.
Pesticide/herbicide application |  |  | X Pesticide Use Permit |  | A PUP is required each year. Permit amendment not needed. Some forests have programatic NEPA done for this pesticide use.
Pulling invasive plants |  | X
Emergency vegetation work |  |  |  | X | See definitions of hazard tree and of emergency vegetation work in Chapter 80 powerline directive
Slash management |  | X |  |  | If piles need to be burned, this may change this to a class C activity.
ACCESS & ROUTE MAINTENANCE
Clear down trees from either USFS road or owner/operator routes | X
Routine maintenance of authorized access trails or roads that are not NFS routes including gates or traffic control devices |  | X
Routine maintenance of authorized access trails or roads that are NFS routes including gates or traffic control devices. |  |  | Road Use Permit required |  | Engineering group issues Road Use Permits.
Motorized travel outside of authorized access routes including unauthorized over snow routes |  |  | X
Non-routine maintenance of access routes that are not NFS routes such as installing gates or bridges. |  |  | X
Emergency access route work including emergency snowplowing |  |  |  | X
Non-emergency snowplowing of utility's roads | X |  |  |  | Class A if addressed in operating plan.
Non-emergency snowplowing of NFS roads | X |  | X |  | Depends on what was addressed in permit and ops plan. If nothing - then engineering would issue a road use permit.
Installation of gates |  |  | X |  | requires a permit amendment
MISC
Other utilties installed onto power poles |  |  | X |  | When power utilities want to allow other entities to install lines on their facilities, the entity must submit proposal to USFS.
Routine substation maintenance | X
Replace substation fencing |  | X
Additonal facilities added within substation footprint |  |  | X
Activity Chart
for Powerline Operating Plans/Agreements
R6 - PNW Region
May 1, 2023
May be edited by forests but should follow law, regulation and policy.