SECTION 01770

- CLOSEOUT PROCEDURES

part - GENERAL

## SUMMARY

#### This Section includes administrative and procedural requirements for contract closeout, including, but not limited to, the following:

##### Inspection procedures.

##### Project Record Documents.

##### Operation and maintenance manuals.

##### Warranties.

##### Instruction of Government personnel.

##### Final cleaning.

#### See Divisions 2 through 16 Sections for specific closeout and special cleaning requirements for products of those Sections.

## SUBSTANTIAL COMPLETION

#### Preliminary Procedures:  Before requesting inspection for determining date of Substantial Completion, complete the following.  List items below that are incomplete in request.

##### Prepare a list of items to be completed and corrected (punch list), the value of items on the list, and reasons why the Work is not complete.

##### Advise Contracting Officer (CO) of pending insurance changeover requirements.

##### Submit specific warranties, workmanship bonds, maintenance service agreements, final certifications, and similar documents.

##### Obtain and submit releases permitting Government unrestricted use of the Work and access to services and utilities.  Include occupancy permits, operating certificates, and similar releases.

##### Prepare and submit Project Record Documents, operation and maintenance manuals, Final Completion construction photographs and photographic negatives, damage or settlement surveys, property surveys, and similar final record information.

##### Deliver tools, spare parts, extra materials, and similar items to location designated by Government.  Label with manufacturer's name and model number where applicable.

##### Make final changeover of permanent locks and deliver keys to CO.  Advise Government personnel of changeover in security provisions.

##### Complete startup testing of systems.

##### Submit test/adjust/balance records.

##### Terminate and remove temporary facilities from Project site, along with mockups, construction tools, and similar elements.

##### Advise CO’s of changeover in heat and other utilities.

##### Submit changeover information related to Government occupancy, use, operation, and maintenance.

##### Complete final cleaning requirements, including touchup painting.

##### Touch up and otherwise repair and restore marred exposed finishes to eliminate visual defects.

#### Inspection:  Submit a written request for inspection for Substantial Completion.  On receipt of request, CO will either proceed with inspection or notify Contractor of unfulfilled requirements.  CO will prepare the Certificate of Substantial Completion after inspection or will notify Contractor of items, either on Contractor's list or additional items identified by CO, that must be completed or corrected before certificate will be issued.

##### Reinspection:  Request reinspection when the Work identified in previous inspections as incomplete is completed or corrected.

##### Results of completed inspection will form the basis of requirements for Final Completion.

## FINAL COMPLETION

#### Preliminary Procedures:  Before requesting final inspection for determining date of Final Completion, complete the following:

##### Submit certified copy of CO’s Substantial Completion inspection list of items to be completed or corrected (punch list), endorsed and dated by CO.  The certified copy of the list shall state that each item has been completed or otherwise resolved for acceptance.

##### Submit evidence of final, continuing insurance coverage complying with insurance requirements.

##### Instruct Government personnel in operation, adjustment, and maintenance of products, equipment, and systems.

#### Inspection:  Submit a written request for final inspection for acceptance.  On receipt of request, CO will either proceed with inspection or notify Contractor of unfulfilled requirements.  CO will prepare a final Certificate for Payment after inspection or will notify Contractor of construction that must be completed or corrected before certificate will be issued.

##### Reinspection:  Request reinspection when the Work identified in previous inspections as incomplete is completed or corrected.

## LIST OF INCOMPLETE ITEMS (PUNCH LIST)

#### Preparation:  Submit three copies of list.  Include name and identification of each space and area affected by construction operations for incomplete items and items needing correction including, if necessary, areas disturbed by Contractor that are outside the limits of construction.

##### Organize list of spaces in sequential order, starting with exterior areas first and proceeding from lowest floor to highest floor.

##### Organize items applying to each space by major element, including categories for ceiling, individual walls, floors, equipment, and building systems.

## PROJECT RECORD DOCUMENTS

#### General:  Do not use Project Record Documents for construction purposes.  Protect Project Record Documents from deterioration and loss.  Provide access to Project Record Documents for CO's reference during normal working hours.

#### Record Drawings:  Maintain and submit one set of blue- or black-line white prints of Contract Drawings and Shop Drawings.

##### Mark Record Prints to show the actual installation where installation varies from that shown originally.  Require individual or entity who obtained record data, whether individual or entity is Installer, subcontractor, or similar entity, to prepare the marked-up Record Prints.

###### Give particular attention to information on concealed elements that cannot be readily identified and recorded later.

###### Record data as soon as possible after obtaining it.  Record and check the markup before enclosing concealed installations.

##### Mark record sets with erasable, red-colored pencil.  Use other colors to distinguish between changes for different categories of the Work at the same location.

##### Note Construction Change Directive numbers, Change Order numbers, alternate numbers, and similar identification where applicable.

##### Identify and date each Record Drawing; include the designation "PROJECT RECORD DRAWING" in a prominent location.  Organize into manageable sets; bind each set with durable paper cover sheets.  Include identification on cover sheets.

#### Record Specifications:  Submit one copy of Project's Specifications, including addenda and contract modifications.  Mark copy to indicate the actual product installation where installation varies from that indicated in Specifications, addenda, and contract modifications.

##### Give particular attention to information on concealed products and installations that cannot be readily identified and recorded later.

##### Mark copy with the proprietary name and model number of products, materials, and equipment furnished, including substitutions and product options selected.

##### Note related Change Orders and Record Drawings, where applicable.

## OPERATION AND MAINTENANCE MANUALS

#### Assemble a complete set of operation and maintenance data indicating the operation and maintenance of each system, subsystem, and piece of equipment not part of a system.  Include operation and maintenance data required in individual Specification Sections and as follows:

##### Operation Data:  Include emergency instructions and procedures, system and equipment descriptions, operating procedures, and sequence of operations.

##### Maintenance Data:  Include manufacturer's information, list of spare parts, maintenance procedures, maintenance and service schedules for preventive and routine maintenance, and copies of warranties and bonds.

#### Organize operation and maintenance manuals into suitable sets of manageable size.  Bind and index data in heavy-duty, three-ring, vinyl-covered, loose-leaf binders, in thickness necessary to accommodate contents, with pocket inside the covers to receive folded oversized sheets.  Identify each binder on front and spine with the printed title "OPERATION AND MAINTENANCE MANUAL," Project name, and subject matter of contents.

## WARRANTIES

#### Submittal Time:  Submit written warranties on request of CO for designated portions of the Work where commencement of warranties other than date of Substantial Completion is indicated.

#### Organize warranty documents into an orderly sequence based on the table of contents of the Project Manual.

##### Bind warranties and bonds in heavy-duty, 3-ring, vinyl-covered, loose-leaf binders, thickness as necessary to accommodate contents, and sized to receive 8-1/2-by-11-inch (115-by-280-mm) paper.

##### Provide heavy paper dividers with plastic-covered tabs for each separate warranty.  Mark tab to identify the product or installation.  Provide a typed description of the product or installation, including the name of the product and the name, address, and telephone number of Installer.

##### Identify each binder on the front and spine with the typed or printed title "WARRANTIES," Project name, and name of Contractor.

#### Provide additional copies of each warranty to include in operation and maintenance manuals.

part 2 – PRODUCTS

## MATERIALS

#### Cleaning Agents:  Use cleaning materials and agents recommended by manufacturer or fabricator of the surface to be cleaned.  Do not use cleaning agents that are potentially hazardous to health or property or that might damage finished surfaces.

part 3 – EXECUTION

## DEMONSTRATION AND TRAINING

#### Instruction:  Instruct Government personnel to adjust, operate, and maintain systems, subsystems, and equipment not part of a system.

##### Provide instructors experienced in operation and maintenance procedures.

##### Provide instruction at mutually agreed-on times.  For equipment that requires seasonal operation, provide similar instruction at the start of each season.

##### Schedule training with Government, through CO, with at least seven day’s advance notice.

##### Coordinate instructors, including providing notification of dates, times, length of instruction, and course content.

#### Program Structure:  Develop an instruction program that includes individual training modules for each system and equipment not part of a system, as required by individual Specification Sections.  For each training module, develop a learning objective and teaching outline.

##### Include instruction for system design and operational philosophy, review of documentation, operations, adjustments, troubleshooting, maintenance, and repair.

## FINAL CLEANING

#### General:  Provide final cleaning.  Conduct cleaning and waste-removal operations to comply with local laws and ordinances and Federal and local environmental and antipollution regulations.

#### Cleaning:  Employ experienced workers or professional cleaners for final cleaning.  Clean each surface or unit to condition expected in an average commercial building cleaning and maintenance program.  Comply with manufacturer's written instructions.

##### Complete the following cleaning operations before requesting inspection for certification of Substantial Completion for entire Project or for a portion of Project:

###### Clean Project site, yard, and grounds, in areas disturbed by construction activities, including landscape development areas, of rubbish, waste material, litter, and other foreign substances.

###### Sweep paved areas broom clean.  Remove petrochemical spills, stains, and other foreign deposits.

###### Rake grounds that are neither planted nor paved to a smooth, even-textured surface.

###### Remove tools, construction equipment, machinery, and surplus material from Project site.

###### Clean exposed exterior and interior hard-surfaced finishes to a dirt-free condition, free of stains, films, and similar foreign substances.  Avoid disturbing natural weathering of exterior surfaces.  Restore reflective surfaces to their original condition.

###### Remove debris and surface dust from limited access spaces, including roofs, plenums, shafts, trenches, equipment vaults, manholes, attics, and similar spaces.

###### Sweep concrete floors broom-clean in unoccupied spaces.

###### Vacuum carpet and similar soft surfaces, removing debris and excess nap; shampoo if visible soil or stains remain.

###### Clean transparent materials, including mirrors and glass in doors and windows.  Remove glazing compounds and other noticeable, vision-obscuring materials.  Replace chipped or broken glass and other damaged transparent materials.  Polish mirrors and glass, taking care not to scratch surfaces.

###### Remove labels that are not permanent.

###### Touch up and otherwise repair and restore marred, exposed finishes and surfaces.  Replace finishes and surfaces that cannot be satisfactorily repaired or restored or that already show evidence of repair or restoration.

            - Do not paint over "UL" and similar labels, including mechanical and electrical nameplates.

###### Wipe surfaces of mechanical and electrical equipment, and similar equipment.  Remove excess lubrication, paint and mortar droppings, and other foreign substances.

###### Replace parts subject to unusual operating conditions.

###### Clean plumbing fixtures to a sanitary condition, free of stains, including stains resulting from water exposure.

###### Replace disposable air filters and clean permanent air filters.  Clean exposed surfaces of diffusers, registers, and grills.

###### Clean light fixtures, lamps, globes, and reflectors to function with full efficiency.  Replace burned-out bulbs, and those noticeably dimmed by hours of use, and defective and noisy starters in fluorescent and mercury vapor fixtures to comply with requirements for new fixtures.

###### Leave Project clean and ready for occupancy.

#### Pest Control:  Engage an experienced, licensed exterminator to make a final inspection and rid Project of rodents, insects, and other pests.  Prepare a report.

#### Comply with safety standards for cleaning.  Do not burn waste materials.  Do not bury debris or excess materials on Government property.  Do not discharge volatile, harmful, or dangerous materials into drainage systems.  Remove waste materials from Project site and dispose of lawfully.

END OF SECTION 01770