SECTION 01330

- SUBMITTAL PROCEDURES

part 1- GENERAL

## SUMMARY

#### This Section includes administrative and procedural requirements for submitting Shop Drawings, Product Data, Samples, and other miscellaneous submittals.

#### See Division 1 Section "Quality Requirements" for submitting test and inspection reports and Delegated-Design Submittals.

#### See Division 1 Section "Closeout Procedures" for submitting warranties Project Record Documents, operation and maintenance manuals and “as builts” drawings.

## DEFINITIONS

#### Action Submittals:  Written and graphic information that requires Contracting Officer’s (CO's) responsive action.

#### Informational Submittals:  Written information that does not require CO's approval.  Submittals may be rejected for not complying with requirements.

## SUBMITTAL PROCEDURES

#### Coordination:  Coordinate preparation and processing of submittals with performance of construction activities.

##### Coordinate transmittal of different types of submittals for related parts of the Work so processing will not be delayed because of need to review submittals concurrently for coordination.

###### CO reserves the right to withhold action on a submittal requiring coordination with other submittals until related submittals are received.

#### Processing Time:  Allow enough time for submittal review, including time for resubmittals, as follows.  Time for review shall commence on CO's receipt of submittal.

##### Initial Review:  Allow 10 days for initial review of each submittal.  Allow additional time if processing must be delayed to permit coordination with subsequent submittals.  CO will advise Contractor when a submittal being processed must be delayed for coordination.

##### If intermediate submittal is necessary, process it in same manner as initial submittal.

##### Allow 10 days for processing each resubmittal.

##### No extension of the Contract Time will be authorized because of failure to transmit submittals enough in advance of the Work to permit processing.

#### Identification:  Place a permanent label or title block on each submittal for identification.

##### Indicate name of firm or entity that prepared each submittal on label or title block.

##### Provide a space approximately [2 by 3 inches] on label or beside title block to record Contractor's review and approval markings and action taken by CO.

##### Include the following information on label for processing and recording action taken:

###### Project name.

###### Date.

###### Name and address of Contractor.

###### Name of manufacturer.

###### Unique identifier, including revision number.

###### Number and title of appropriate Specification Section.

###### Drawing number and detail references, as appropriate.

###### Other necessary identification.

#### Deviations:  Highlight, encircle, or otherwise identify deviations from the Contract Documents on submittals.

#### Additional Copies:  Unless additional copies are required for final submittal, and unless CO observes noncompliance with provisions of the Contract Documents, initial submittal may serve as final submittal.

#### Use for Construction:  Use only final submittals with mark indicating action taken by CO in connection with construction.

part 2 – PRODUCTS

## ACTION SUBMITTALS

#### General:  Prepare and submit Action Submittals required by individual Specification Sections.

##### Number of Copies:  Submit three copies of each submittal, unless otherwise indicated.  CO will return two copies.  Mark up and retain one returned copy as a Project Record Document.

#### Product Data:  Collect information into a single submittal for each element of construction and type of product or equipment.

##### If information must be specially prepared for submittal because standard printed data are not suitable for use, submit as Shop Drawings, not as Product Data.

##### Mark each copy of each submittal to show which products and options are applicable.

##### Include the following information, as applicable:

###### Manufacturer's written recommendations.

###### Manufacturer's product specifications.

###### Manufacturer's installation instructions.

###### Manufacturer's catalog cuts.

###### Wiring diagrams showing factory-installed wiring.

###### Compliance with recognized trade association standards.

###### Compliance with recognized testing agency standards.

#### Shop Drawings:  Prepare Project-specific information, drawn accurately to scale.  Do not base Shop Drawings on reproductions of the Contract Documents or standard printed data.

##### Preparation:  Include the following information, as applicable:

###### Dimensions.

###### Identification of products.

###### Fabrication and installation drawings.

###### Roughing-in and setting diagrams.

###### Wiring diagrams showing field-installed wiring, including power, signal, and control wiring.

###### Notation of dimensions established by field measurement.

##### Wiring Diagrams:  Differentiate between manufacturer-installed and field-installed wiring.

#### Samples:  Prepare physical units of materials or products, including the following:

##### Samples for Initial Selection:  Submit manufacturer's color charts consisting of units or sections of units showing the full range of colors, textures, and patterns available.

## INFORMATIONAL SUBMITTALS

#### General:  Prepare and submit Informational Submittals required by other Specification Sections.

##### Number of Copies:  Submit two copies of each submittal, unless otherwise indicated.  CO will not return copies.

##### Certificates and Certifications:  Provide a notarized statement that includes signature of entity responsible for preparing certification.  Certificates and certifications shall be signed by an officer or other individual authorized to sign documents on behalf of that entity.

##### Test and Inspection Reports:  Comply with requirements in Division 1 Section "Quality Requirements."

#### Contractor's Construction Schedule:

##### The following submittal is required following award of contract for review and/or approval pursuant to contract provisions:

| ##### Item Description | ##### Copies Required | ##### References |
| --- | --- | --- |
| ##### Cost breakdown schedule listing main types of work and totaling amount of contract | ##### 1 | ##### FAR 52.232-05 |

#### Material Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting test results of material for compliance with requirements.

#### Field Test Reports:  Prepare reports written by a qualified testing agency, on testing agency's standard form, indicating and interpreting results of field tests performed either during installation of product or after product is installed in its final location, for compliance with requirements.

#### Maintenance Data:  Prepare written and graphic instructions and procedures for operation and normal maintenance of products and equipment.  Comply with requirements in Division 1 Section "Closeout Procedures."

#### Manufacturer's Instructions:  Prepare written or published information that documents manufacturer's recommendations, guidelines, and procedures for installing or operating a product or equipment.  Include name of product and name, address, and telephone number of manufacturer.

part 3 – EXECUTION

## general

#### Review each submittal and check for compliance with the Contract Documents.  Note corrections and field dimensions.  Mark with approval stamp before submitting to CO.

#### Approval Stamp:  Stamp each submittal with a uniform, approval stamp.  Include Project name and location, submittal number, Specification Section title and number, name of reviewer, date of Contractor's approval, and statement certifying that submittal has been reviewed, checked, and approved for compliance with the Contract Documents.

#### CO will not review submittals that do not bear Contractor's approval stamp and will return them without action.

#### Submittals not required by the Contract Documents will not be reviewed and may be discarded.

END OF SECTION 01330