SECTION 01200

MOBILIZATION payment procedures

# Part 1 - GENERAL

## summary

### This work shall consist of preparatory work and operations necessary for the movement of personnel, equipment, supplies, and incidentals to the project site, and for all other work and operations that must be performed or that cause costs to be incurred prior to beginning work on the various items on the project site.

# Part 2 - products (not used)

# Part 3 - execution (not used)

# Part 4 - measurement and Payment

## Progress payments will be made as follows:

### When 5 percent or more of the original contract amount is earned from other pay items, 50 percent of the amount for mobilization, or 5 percent of the original contract amount, whichever is less, will be paid.

### When 10 percent or more of the original contract amount is earned from other pay items, 100 percent of the amount for mobilization, or 10 percent of the original contract amount, whichever is less, will be paid.

### Upon completion of all work on the project, any unpaid amount for mobilization will be paid.

### The total of all payments shall not exceed the original contract amount for this item.

## basis of payment

### Payment will be made under:

PAY ITEM	DESCRIPTION	PAY UNIT

01200-1	Mobilization	Lump Sum

END OF SECTION